## Roadmap
ID | Priority | Status | Area | Title | Description | Source | Created On | Owner | Link
CM-001 | P0 | Done | Mosaic | Mosaic detection/restoration pipeline | End-to-end mosaic restoration inherited from the gSwapper/gRestorer lineage: YOLO detection (lada model family) -> tracker -> BasicVSR++ restoration -> paste-back. Foundation ChitraMaya is built on. Ported from gSwapper RM-001. | Ported | 2026-06-30
CM-002 | P0 | Done | Mosaic | BasicVSR++ TRT sub-engine compilation | Six sub-engines (4 loop_body + preprocess + upsample) compiled via torch_tensorrt dynamo. tools/compile_basicvsrpp.py. Ported from gSwapper RM-002. | Ported | 2026-06-30
CM-003 | P0 | Done | Detection | YOLO TRT compilation path | tools/compile_yolo.py: ultralytics export with dynamic=True (avoids fp16/fp32 input cuTensor crash). Engines -> models/engines/<stem>.engine. YOLO11m-seg needs --max-batch 8 not 16 (batch 16 exceeds 2GB workspace at ~2.1GB scratch). Ported from gSwapper RM-003. | Ported | 2026-06-30
CM-004 | P0 | Done | Detection | AutoBackend dtype-sync fix for TRT engines | ultralytics TRT engines declare FLOAT input bindings even when weights are fp16; feeding fp16 produced silent garbage detections. Read self.model.fp16 post-init instead of the constructor param. Ported from gSwapper RM-004. | Ported | 2026-06-30
CM-005 | P1 | Done | Detection | Detector imgsz/conf defaults (640/0.15) | Detection-count discrepancy vs Lada CLI traced to --det-imgsz and --det-conf mismatches. Ported from gSwapper RM-005; directly informs the SBS downscale analysis (CM-014). | Ported | 2026-06-30
CM-006 | P1 | Done | Infra | ASCII-safe stdout + UTF-8 I/O convention | stdout-bound strings ASCII-only (comments/docstrings keep Unicode); subprocess text=True calls pass encoding='utf-8', errors='replace'. Prevents cp1252 crashes on Windows. Ported from gSwapper RM-008/RM-009. | Ported | 2026-06-30
CM-007 | P1 | Done | Infra | Compile-All-Engines.ps1 multi-model discovery | Auto-discovers *.pt (detection) and *.pth (restoration); safer defaults (DetImgsz 640, DetMaxBatch 8, DetWorkspace 2GB); skips known non-BasicVSR++ checkpoints. The script Model Management (CM-029) will drive. Ported from gSwapper RM-010. | Ported | 2026-06-30
CM-008 | P2 | Done | Infra | Engines unified under models/engines/ | Detection + YOLO engines live in models/engines/. (BasicVSR++ sub_engines relocation still open - CM-037.) Ported from gSwapper RM-011. | Ported | 2026-06-30
CM-009 | P2 | Done | Infra | Dependencies authoritative in requirements.txt | Runtime deps in requirements.txt (PEP 621 can't express --extra-index-url for +cu128 wheels); pyproject.toml keeps metadata + entry point. Ported from gSwapper RM-012. | Ported | 2026-06-30
CM-010 | P1 | Done | Infra | Split gSwapper -> ChitraMaya (mosaic product) | Mosaic restoration split into its own product/repo (seatv persona), gSwapper remaining face-swap-focused (ViniMaya/mountlord). Realizes gSwapper RM-028. Strict no-model-shipping policy: code + compile-all script, editable install only. | CM-Decision | 2026-06-30
CM-011 | P0 | Done | Mosaic | Drop 1: Restore & Save -> Preview | Full-restore completion enables Preview playback of the output; _preview_is_temp guard prevents /api/clear-preview from ever deleting the deliverable (only deletes segment temp). | CM-Decision | 2026-07-05
CM-012 | P0 | Done | UI | Drop 2: face-swap chrome teardown | Deleted the left face-library panel, moved Output/Temp folder fields to the header, repurposed the strip (Target->Mosaic, Swapped->Restored). Removed Source/Apply-to-All/nav/Live. Dormant detect/zoom flow preserved for Drop 3. | CM-Decision | 2026-07-05
CM-013 | P0 | Done | Mosaic | Drop 2a: Split SBS per-eye detection | Single 'Split SBS' checkbox in Detection sets sbs_enabled + sbs_det_split (per-eye split, position-preserving) and the seam guard (prevents a restoration crossing the eye midline). [SBS] log lines. Realizes gSwapper RM-013. | CM-Decision | 2026-07-06
CM-014 | P1 | Done | Detection | SBS detection win (110 -> 1046 frames, 0 miss) | On every-frame-mosaic VR content, flat detection covered 110/1046 frames; per-eye SBS covers 1046/1046 with 0 visible miss. Root cause: detector imgsz 640 letterboxes 4320-wide flat = 6.75x downscale (mosaics vanish); per-eye 2160->640 = 3.375x. ~17% wall overhead, effectively free (pipeline is CPU-decode-bound). Split SBS = correct default for the target library. | Claude Analysis | 2026-07-06
CM-015 | P1 | Done | Mosaic | Clip stats ([ClipStats] + .misses JSON) | Per-run clips, total_clip_frames (frames fed to the restorer), and len min/med/max/mean, in the console line and the misses JSON. total_clip_frames predicts restore cost far better than box count - it exposed the memory-pressure confound (CM-017). | CM-Decision | 2026-07-06
CM-016 | P0 | Done | Infra | VRAM leak fix on pipeline rebuild | MosaicPipeline.close() only nulled refs; TRT contexts (held in cycles) lingered. Now gc.collect() + torch.cuda.empty_cache() + ipc_collect(). Verified flat at 1356 MiB across four sequential config-change rebuilds (was climbing 1356->3327->5297->7268 and hanging on run 3). Was silently corrupting every back-to-back measurement. | Claude Analysis | 2026-07-06
CM-017 | P1 | Done | Testing | 'vr faster than lada' myth busted | Yesterday's 'vr detector restores faster' conclusion was a pure run-order memory-pressure artifact (CM-016): on a fresh GPU both restore at ~14 ms/clip-frame with near-equal total_clip_frames. Both SBS configs hit 0 visible miss, so detector choice reduces to headset visual quality, not speed. | CM-Testing | 2026-07-07
CM-018 | P0 | Done | FOI | Drop 3: Test Frame windowed preview | Restore a window around the playhead and show each detected region as [Mosaic ¦ Restored]. Capture-tap in run() snapshots the target frame's boxes + pre-composite (Mosaic) + post-composite paste-back (Restored) during the REAL pass (WYSIWYG); additive + guarded (byte-identical when foi_capture=None). Dedicated /api/mosaic-foi endpoint; discard encoder skips NVENC + mux. | CM-Decision | 2026-07-07
CM-019 | P1 | Done | FOI | Test Frame trim fix (NVDEC-clean, frame-exact) | Window extract cuts by exact -frames:v (not -t, which cut mid-GOP and left broken refs) and uses crf 10 - NOT crf 0: lossless H.264 uses transform-bypass macroblocks that Ampere NVDEC decodes unreliably ('Decode Error occurred for picture N'). yuv420p + bf 0; half-frame seek bias so CFR rounding can't skip the start frame. Stays on NVDEC (same decode path as a real run). | Claude Analysis | 2026-07-08
CM-020 | P1 | Done | FOI | Enlarge over the player (ViniMaya-style) | Enlarge reuses the center-area zoom overlay (absolute inset:0 in .center-area) so side controls stay visible - not a full-screen lightbox. Strip stays as picker; panels flex-fill the actual player box (sized to center-area, not viewport) with object-fit:contain, aspect preserved, live in windowed + fullscreen. Refreshes in place on re-run. | CM-Decision | 2026-07-08
CM-021 | P2 | Done | FOI | Test Frame footer button + button-as-indicator | Repurposed the dormant 'Detect' footer button (restoreDetectBtn) as 'Test Frame N' (label tracks playhead), primary shade to group with Restore. Button is the sole working indicator (disabled + 'Refreshing...' during run) - no modal, so the images stay visible for before/after. Disabling during the run fixes the second-click busy race. | CM-Decision | 2026-07-09
CM-022 | P1 | Done | UI | Saved model selections restored on load | Startup race: config-load applyConfig set the model dropdown value before populateMosaicModelDropdowns filled the options -> silent no-op -> user forced to re-pick. Fixed by stashing the saved values (window._pendingMosaicModels) and having populate restore them via fill()'s savedValue. Robust to either resolve order. | Claude Analysis | 2026-07-09
CM-023 | P2 | Done | Decode | ffmpeg decode-flags investigation (settled) | -threads 0 -thread_type frame+slice measured ~3.6% (139s->134s) = run-to-run noise; ffmpeg already frame-threads H.264/HEVC by default and slice is a no-op on single-slice streams. Real 8K decode lever is Blackwell NVDEC (Ampere eGPU caps at 4096 wide -> CPU fallback). Not adopted. | CM-Testing | 2026-07-07
CM-024 | P1 | Done | Packaging | PyInstaller onedir package | Realizes gSwapper RM-025. Modeled on the working gRestorer spec: bootstrap entrypoint (avoids relative-import crash) + runtime PATH hook (resolves CUDA/TRT/PyNvVideoCodec DLLs + bundled ffmpeg) + collect_dynamic_libs. Adds the GUI stack the CLI didn't need (pywebview/pythonnet/clr_loader, static/templates) + tools + TensorRT. Fixes the 3 causes the prior packager failed on. | CM-Decision | 2026-07-08
CM-025 | P1 | Done | Packaging | torch_tensorrt bundling fix | Restorer engine loader (basicvsrpp trt_export._mute_torch_tensorrt) imports torch_tensorrt; excluding it (wrong 'raw TRT only' assumption) crashed Test Frame at restorer build on the clean machine. Removed from excludes + collect_submodules/collect_dynamic_libs. Detection (raw TRT) passed; only the restorer build tripped. | Claude Analysis | 2026-07-08
CM-026 | P1 | Done | Packaging | TRT builder-resource arch trim (~1.45 GB) | tensorrt_libs bundles a per-arch nvinfer_builder_resource_sm<ARCH>_10.dll (150-640 MB each). Ship only tested consumer archs sm_120 + sm_89 + sm_86, plus the PTX builder (JIT fallback so untested/newer GPUs still compile, slower). Drop datacenter/untested sm_90/sm_100/sm_80/sm_75. Filter runs on a.binaries post-Analysis; denylist var for per-release tuning. 3.2 GB -> 1.77 GB. | Claude Analysis | 2026-07-08
CM-027 | P1 | Done | Packaging | Installer volume splitting under 2 GB | torch (4 GB) + tensorrt_libs make 2 GB unreachable without fragile pruning, so ship split: 7z SFX -v1900m volumes (.001/.002) under GitHub's 2 GB release-asset cap. -SplitMB param in packager.ps1. | CM-Decision | 2026-07-08
CM-028 | P1 | Done | Testing | Clean-machine validation (6 GB 3060) | Split installer ran on a different 6 GB 'Frankenstein' 3060: 4K + wide SBS, Preview + full Restore all working. Confirms the package is functional on modest consumer hardware. | CM-Testing | 2026-07-08
CM-029 | P1 | Done | Infra | Model Management window | Manage Models modal: source-URL dropdown (seeded with ladaapp + zelefans HF repos, learns user-added, persists to model-sources.json) -> fetch via HF list_repo_files -> multi-select picker -> Compile, driving Compile-All-Engines.ps1 (CM-007) with the compile log streamed into a pane. v1 shells out to the PS1 (don't re-port hard-won compile flags). Last blocker for fresh installs (no engines shipped). https://huggingface.co/zelefans DONE (field-verified: download + compile on 5060Ti / 3060 12GB / 3060 6GB / 4060 8GB; the HF-403 download hardening is CM-060). Two corrections to the original spec: it drives the exe's -compile-det/-compile-rest subcommands directly (not the PS1 - same flags, no PowerShell dependency), and it is no longer a fresh-install blocker. Residual Manage-Models poll polish tracked as CM-065. | Roadmap | 2026-07-09
CM-030 | P2 | Open | Infra | GPU-arch detection + unsupported-GPU message | In the compile flow, detect the running sm_XX; if no matching native builder and no PTX, fail with a clear 'GPU architecture sm_XX not supported in this build' message rather than a raw TRT crash. With PTX shipped (CM-026) this degrades to slow-compile instead of erroring, but the check belongs there. Ties to Model Management. | Roadmap | 2026-07-09
CM-031 | P1 | Open | Decode | Windowed SimpleDecoder pipeline (shared core) | Separate windowed pipeline for Test Frame + Restore-segment sharing the detect->track->restore->composite CORE with full Restore (orchestration differs: streaming+encode vs windowed+capture). Uses PyNvVideoCodec 2.1 SimpleDecoder.get_batch_frames_by_index([Fs..Fe]) (verified 121 frames in 0.32s, ~50x vs the ffmpeg temp-clip's ~16s), frame-exact. Retires the temp-clip cut, kills the crf-10 decode errors + transcode variance. Full Restore keeps ThreadedDecoder (NVIDIA-recommended for sequential throughput). Adapter presents the same read_batch() so run() is untouched; RGBP format-match assumed with a fail-fast tripwire on first batch; wide-HEVC on sub-50-series eGPUs needs an -ss ffmpeg fallback. REVIEW (CM-049): design holds; recommend extracting a RestorationCore (detector+tracker+restorer+compositor+FrameStore) with two thin runners (StreamingRunner / WindowedRunner) so Test Frame, segment-restore AND the misses-report all consume the windowed path; collapses _DiscardEncoder + the 5 foi_capture hooks. Include segment-restore in the same change (it still has the temp-clip round trip). Answer the CM-032 warm-detector question first. | CM-Decision | 2026-07-09
CM-032 | P2 | Done | FOI | Bug: Test Frame regions accumulate across runs | On an SBS frame (4 regions), repeated Test Frames showed 4 -> 8 -> 12 rows. Client renders correctly (clears before rebuild), so res.regions itself grows server-side = warm-pipeline state bleed across runs. Same root cause as the ROI-growth / runtime non-determinism (same frame, different avg_roi_area_px run-to-run). Fixed for free by CM-031 (fresh isolated pipeline per Test Frame). Awaiting consistent repro on the installed build. INVESTIGATION (Critical Review, CM-049): ruled out the tracker, FrameStore, DetStats and the FOI capture dict (all rebuilt per run). Remaining prime suspect = the WARM detector's Ultralytics AutoBackend TRT binding-buffer reuse across runs (window batches force an 8->1->8 shape churn at each run boundary). NOTE: CM-031's per-run pipeline does NOT auto-fix this — the detector stays warm across runs — so carry a detector-level reset (or fixed-shape batching) into it. Cheap interim mitigations: dedupe identical boxes in mosaic_foi_preview; pad the window so n_window % batch_size == 0. UPDATE 2026-07-28: fixed -- the strip rebuilds in place on every run; Batch 28's per-frame history stack is intentional accumulation (cap 5, cleared on frame change). | Claude Analysis | 2026-07-09
CM-033 | P2 | Open | Decode | .ts source scrubbing (rewrap to mp4 on load) | WebView2/Chromium <video> can't scrub MPEG-TS (.ts); only .mp4. Processing via ffmpeg is unaffected. On load of a non-mp4/unsupported container, losslessly rewrap to a temp .mp4 (ffmpeg -c copy) and point the PLAYER at that while detect/restore/FOI keep using the original path. Needed for Test Frame playhead-parking on raw VR .ts sources. | Claude Analysis | 2026-07-09
CM-034 | P2 | Open | Packaging | torch CUDA-lib pruning (post-release) | torch is ~4 GB (bundled cuDNN/cuBLAS/cuFFT/cuSPARSE/cuSOLVER). Potential ~1.5 GB (cuDNN alone) if unused at runtime. Fragile - prune only with evidence: run a full Restore + Test Frame and check (Get-Process ChitraMaya).Modules for which CUDA DLLs actually load before dropping. Off the critical path; do after first release. | Roadmap | 2026-07-09
CM-035 | P3 | Open | FOI | Cancel behaviour during Test Frame | The progress/modal Cancel is wired to the full-restore cancel path; a Test Frame is synchronous and can't truly cancel. Hide or relabel Cancel in Test-Frame context to avoid a confusing state. | Roadmap | 2026-07-09
CM-036 | P3 | Done | UI | Gray out inert controls when precision baked | FP16 flag is inert on a single-precision .engine (ultralytics AutoBackend declares FLOAT input bindings regardless); Max Clip is inert once the sub-engine set is compiled. Gray them out when inapplicable so the UI doesn't imply a live knob. DONE (Fix Batch 4): Feather grays out unless Blend Mask=FaceFusion; Mask Colour/Opacity gray unless Preview Mask Only; Detection FP16 grays when a compiled detection .engine is selected (baked precision). Restoration FP16 left LIVE — it selects the fp16-vs-fp32 engine set, not a runtime cast. | Roadmap | 2026-07-09
CM-037 | P2 | Open | Mosaic | Move BasicVSR++ sub_engines into models/engines/ | Relocate models/<stem>_sub_engines/ -> models/engines/<stem>_sub_engines/ for consistency with the YOLO/detection convention. Requires runtime loader path changes. Ported from gSwapper RM-014. | Ported | 2026-07-09
CM-038 | P1 | Open | Mosaic | Temporal crossfade at clip boundaries | Smoother transitions between restored clips and source at boundaries. Deferred 'until TRT restoration works' - condition now met. Ported from gSwapper RM-015. UPDATE 2026-07-28: alternative under consideration -- extend the CM-078 stabilizer across clip boundaries (carry the previous clip's last stabilized frames into the next window for the same track). Decision pending full-video watch at MCL 60 + TS on: visible seams -> design it; none -> drop. | Ported | 2026-07-09
CM-039 | P3 | Open | Mosaic | --color-match flag for color transfer | Opt-in color-match between restored crop and surrounding context; gate on successful restoration before applying (root cause of paste-back artifacts identified). Ported from gSwapper RM-016. | Ported | 2026-07-09
CM-040 | P3 | Open | Mosaic | max_clip_length 120/180 visual A/B | Quality sweep at higher mcl values (engines encode the size in the filename, so they coexist). Ported from gSwapper RM-017. | Ported | 2026-07-09
CM-041 | P2 | Open | Testing | Real-world benchmark with NMS-timeout patch | The max_time_img=0.3 NMS-timeout patch in lada_yolo.py was validated only on synthetic (PurpleRain/eggplant). Stress-test on real-world VR video to confirm no regressions. Ported from gSwapper RM-018. | Ported | 2026-07-09
CM-042 | P2 | Open | Mosaic | VRAM-aware batch sizing | Dynamic batch sizing based on available VRAM to maximize throughput per machine (3060/3060Ti/3060 12GB/5060 Ti fleet). Deferred until the basic TRT path was stable - now met. Ported from gSwapper RM-019. | Ported | 2026-07-09
CM-043 | P1 | Open | Testing | 5060 Ti Blackwell perf revisit (TRT 10.16+) | TRT 10.15 picks suboptimal kernels for sm_120 (Blackwell) - 5060 Ti slower than 3060 12GB on mosaic despite newer arch. Revisit when TRT 10.16+ is validated against the rest of the venv stack. Ported from gSwapper RM-020. | Ported | 2026-07-09
CM-044 | P3 | Open | Mosaic | Evaluate zelefans VR restoration models | VR-specific BasicVSR++ weights that compile cleanly through the existing sub_engines pipeline (same arch). Pull latest from https://huggingface.co/zelefans and run side-by-side (v0.2 vs v0.5 vs generic) on VR content to pick the default. Ported from gSwapper RM-032. | Ported | 2026-07-09
CM-045 | P1 | Done | Mosaic | Borrow zelefans VR transformation logic | ladaapp isn't pursuing VR; zelefans maintains vr_remove_mosaic (https://codeberg.org/zelefans/vr_remove_mosaic) with VR-specific geometric/projection frame transforms worth adopting into our SBS path. Study + integrate. Ported from gSwapper RM-033. UPDATE: shipped as Batch 19 VR projection (per-eye hequirect->fisheye; detection/tracking/restoration run in fisheye space; inverse-warp paste-back). Projected EOF-flush gap fixed in Batch 26. | Ported | 2026-07-09
CM-046 | P3 | Done | UI | Custom modal dialog (replace confirm/alert) | showDialog(title, msg) for all popups - custom styled, not browser-native. Ported from gSwapper RM-026. ¦¦ UPDATE 2026-09-11: Shipped: showConfirm()/modal overlay replaces confirm/alert (Batch 13 modal work; used by presets delete, Reset Defaults). v1.70.00. | Ported | 2026-07-09
CM-047 | P3 | Open | Infra | Stamp models/engines/ with build metadata | Write build_info.json after each compile: hostname, GPU model, TensorRT version, compile date, per-engine compile time + scratch memory. Diagnoses cross-machine perf differences and which machine built which engines. Ties to Model Management (CM-029). Ported from gSwapper RM-031. ¦¦ UPDATE 2026-09-11: Superseded by CM-151 (engine manifest with build stamp + provenance). | Ported | 2026-07-09
CM-048 | P3 | Open | Infra | Document Windows codepage convention | One-line note in CONTRIBUTING: any text I/O must specify encoding='utf-8'; subprocess text=True also passes errors='replace'. Prevents recurrence of the cp1252 bug family. Ported from gSwapper RM-029. | Ported | 2026-07-09
CM-049 | P0 | Done | Review | Critical architecture/design/code review of v1.0 | Full external review (Claude) of architecture, pipeline correctness, concurrency/lifecycle, API/abstraction quality and the windowed-refactor design. Produced the fix backlog realized in CM-050..060 and the roadmap items CM-061..064; re-scoped CM-031/CM-032/CM-036. Deliverables: ChitraMaya-CriticalReview.md, ChitraMaya-WiringAudit.md. | Claude Analysis | 2026-07-12
CM-050 | P0 | Done | Decode | Segment-preview crf-10 fix (extends CM-019) | mosaic_segment extracted its temp clip at crf 0 (lossless H.264 transform-bypass -> Ampere NVDEC 'Decode Error occurred for picture N'), the exact bug CM-019 fixed for Test Frame but never applied here. Switched to the CM-019 recipe: crf 10, yuv420p, -bf 0, frame-exact -frames:v cut. Fix Batch 1. Field-verified. | Claude Analysis | 2026-07-12
CM-051 | P0 | Done | Mosaic | Tracker gap-fill buffer clone (double-restore fix) | SceneTracker's gap-fill ring buffer stored REFERENCES to frames the compositor mutates in place; a scene reactivating within its TTL window could gap-fill from already-restored pixels and re-restore them (soft smearing near overlapping-scene clip boundaries). Now clones on insert (the docstring already promised it). One-line, within the stated memory budget. Fix Batch 1. | Claude Analysis | 2026-07-12
CM-052 | P0 | Done | Encode | AsyncEncoder deadlock + cleanup-ordering fix | Root cause of the historical 'UI hangs on long restores': the NVENC worker dying (e.g. error 8) while the main thread blocked on a full queue -> infinite hang holding _op_lock. Now a bounded put() re-checks the worker error (fail-fast <=250ms); run()'s finally re-raises the producer error AFTER cleanup so the encoder/NVENC session/partial remux are never stranded. FIELD-VERIFIED: first live NVENC error 8 failed fast + 'lock released', no hang. Fix Batch 1 (+ Batch 5v3 guarded cleanup salvaging partial output). | Claude Analysis | 2026-07-12
CM-053 | P1 | Done | UI | Frontend state fixes (segment/preview + model dropdowns) | loadVideo() now resets segment marks + preview state on every video load (was: a segment marked on video A silently submitted A's time range against video B). _pendingMosaicModels is consume-once and only stashed on an actual apply-miss (was: finishing any compile/download reverted both model dropdowns to the startup config's models). Refines CM-022. Fix Batch 1. | Claude Analysis | 2026-07-12
CM-054 | P1 | Done | Mosaic | Dynamic-engine clip-size resolution (Max Clip flexible) | Compiled sub-engine sets are dynamic (valid 1..N), so the compiled size should only pick which files to load while the request stays the runtime ceiling. Any Max Clip <= largest compiled size now runs: loads the smallest covering set and runs at the requested value; caps only when nothing bigger exists. UI slider no longer locked to exact compiled sizes; CLI no longer hard-fails or silently drops to PyTorch on mismatch. Single source: engine_paths.pick_engine_clip_size() across CLI/server/UI. Fix Batch 1. Field-verified. | Claude Analysis | 2026-07-12
CM-055 | P1 | Done | Infra | Install-dir path resolution (double-click launch) | api_list_mosaic_models, in-app model download, and config read/write were resolved relative to the process CWD -> EMPTY model dropdowns when launched by double-click / a shortcut / from any folder other than the install dir (only the .cmd launcher's chdir made it work). Now anchored to _app_base_dir() (exe dir when frozen, cwd from source). Also initialises faces_dir='' (fresh-launch AttributeError). Fix Batch 2. Field-verified on all machines. | Claude Analysis | 2026-07-13
CM-056 | P1 | Done | Infra | Knob wiring audit + fixes + import-time guardrail | End-to-end audit of every UI control and CLI flag (ChitraMaya-WiringAudit.md; 11 broken knobs). Fixed: Detection Batch (silently always 8); Feather + Blend Mask (never reached the compositor -> now functional, incl. FaceFusion shape-aware soft edge via create_support_blend_mask); --mux-extra-args / --mp4-fast-start. Removed 6 decorative CLI flags. Guardrail: every MosaicPipelineConfig field must be classified consumed/inert (unclassified or renamed -> raises at import) + runnable tools/verify_wiring.py (15 round-trip checks). Fix Batch 3. | Claude Analysis | 2026-07-13
CM-057 | P2 | Done | UI | Run visibility (batch_size log + Feather overlay) | [Pipeline] batch_size=N now logged so Detection Batch / --batch-size / --det-batch-size are verifiable. Progress-overlay shows Feather only when Blend Mask=FaceFusion (was implying it was active under Blend Mask=None). Fix Batch 4. | Claude Analysis | 2026-07-13
CM-058 | P0 | Done | Infra | VRAM oversubscription warning + VRAM-aware FrameStore | Pre-flight at run start: driver-level free VRAM (mem_get_info, counts TRT allocations) vs FrameStore + a resolution/queue-aware surface reserve. Tiers: SEVERE (even the one-clip floor doesn't fit -> 'does not fit this GPU') / OVERSUBSCRIBED (auto store reduced toward fit) / THIN / silent. Names the levers, including which smaller compiled engine set a lower Max Clip would select. Guarded crash cleanup salvages the partial output and surfaces the ORIGINAL error; poisoned-CUDA-context restart hint in the UI. Field-verified on 8GB (b180 -> SEVERE, correct). Fix Batch 5 v3. Relates CM-042. | Claude Analysis | 2026-07-13
CM-059 | P1 | Done | Encode | Async encoder opt-in (synchronous default) | The async NVENC thread produced two field failure modes on VRAM-tight cards (hangs [fixed, CM-052] and NVENC error 8 under saturation), while sync has been reliable. Sync is now the DEFAULT (also frees the ~500-600MB BGRA queue at 4K); async is opt-in via a new UI 'Async Encode' checkbox / --async-encoder for ~20-25% on encode-heavy runs with VRAM headroom. Fix Batch 6. | CM-Decision | 2026-07-13
CM-060 | P1 | Done | Infra | Hugging Face download 403 fix | HF's CDN began rejecting the downloader's bare 'ChitraMaya' User-Agent (WAF bot filtering; huggingface.co served the 302, the CDN 403'd). Fixed by proper identification (ChitraMaya/1.1 +repo URL) - FIELD-CONFIRMED (instant recovery from the same IP, no token). Added as belt-and-braces: optional access token (hf-token.txt / HF_TOKEN, not stored in config.json), safe manual redirect handling (bearer sent to huggingface.co only, dropped at the CDN), and actionable rate-limit error text. Fix Batch 7. | Claude Analysis | 2026-07-14
CM-061 | P1 | Done | Detection | Detection Image Size UI control (R1) | Run-time detection imgsz is hardwired to 640 on the UI path (MosaicConfig has no field; to_pipeline_config never sets it). 960-imgsz detection is CLI-only (--det-imgsz). Add a Detection Image Size dial to the Control Panel, wire it through MosaicConfig + the pipeline rebuild key, and snap/select to the selected detection engine's compiled size (as Max Clip does for restoration; a .pt is dynamic). Unblocks the 640-vs-960 comparison from the UI. From CM-049. ¦¦ UPDATE 2026-09-11: Shipped: Detection Image Size dial (Batch 17, v1.20/1.30); CM-148 submit-time mismatch modal added v1.70.00. | Claude Analysis | 2026-07-14
CM-062 | P2 | Open | Mosaic | Dynamic MCL + Img Size engine strategy (R2 - investigate) | Decide the engine-profile strategy. Restoration: per-size EXACT sets (less resident VRAM + tuned kernels; current 8GB recommendation) vs a single WIDE set with opt at the common size (note the unused OPT_DYNAMIC_BATCH=60 constant; only preprocess/upsample vary with N - the 4 loop-body engines are batch-1 static and SHARED across sets, so extra sizes are cheap). Measure the off-opt penalty empirically (A/B: MCL 60 via b60 vs b180, compare t_restore). Decide what Manage Models compiles by default and how the resolver + UI constraints present it. Detection: same question for imgsz (640 vs 960 are separate engines). Extends CM-040; ties to CM-061. From CM-049. ¦¦ UPDATE 2026-09-11: Largely superseded: v1.60 fixed-batch sub-engines serve any Max Clip (CM-104); per-size detection engines remain in CM-151. | Claude Analysis | 2026-07-14
CM-063 | P3 | Open | Encode | Remux passthrough knobs (--mux-keep-subs, audio codec) | --mux-keep-subs and --mux-audio copy/aac parse but aren't honored (never passed to Encoder; audio collapses to stream-copy). Wire into the remux command builder - needs on-hardware ffmpeg testing given the delicate A/V start-offset branches. Deferred out of Fix Batch 3 for safety. From CM-049. | Claude Analysis | 2026-07-14
CM-064 | P2 | Done | UI | Console/window UX (windowed build + attach-console) | Closing the console window kills the server (built console=True). Build console=False (windowed) + a Windows AttachConsole(parent) shim so CLI subcommands still stream to their terminal + a rotating log file, so a UI launch has no closable terminal to kill by accident. Needs packaged-build testing. From CM-049. UPDATE: shipped as Batch 24 windowed build -- two bootloaders (ChitraMaya.exe windowed + ChitraMaya-cli.exe console), in-app Console drawer (close fix Batch 26c), ChitraMaya-console.log with rotation (25b). | Claude Analysis | 2026-07-14
CM-065 | P3 | Done | UI | Manage Models poll-lifecycle fixes | Two Manage-Models UI bugs from CM-049. (1) closeManageModels() cleared only the compile poll (_mmPoll), not the download poll (_mmDlPoll) - a download poll kept firing every 800ms against the hidden modal after close; now clears BOTH. (2) Compile and download share the single #mmLog pane (and the GPU): extracted _mmStartDlPolling() so a running download resumes on reopen (was: only compile resumed), and added a guard so the two can't run concurrently (their logs would overwrite each other tick-by-tick). Fix Batch 8. | Claude Analysis | 2026-07-14
CM-066 | P1 | Done | SBS | SBS View - projected 3D compare viewer | Projected equirect-180 per-eye viewer on the main player (SBS button): drag look-around + wheel zoom, Eye L/R, View Original/Restored/Wipe with draggable divider, frame-locked A/B sync (playbackRate-nudge; hard-seek only on jumps), full transport with frame stepping + app skip amounts, 0.1-1x speed, segment-preview clock offset, Esc frees decoders. three.js r185 vendored (module+core). Shipped v1.10.00 (Batch 10 + transport/view/sync drops). | Gman + Claude | 2026-07-17
CM-067 | P1 | Done | Mosaic | Add Mosaic (manual) - draw rectangles + pixelate (SFW censor) | Pixelate up to 3 regions and save (-mosaic.mp4 / -mosaic-seg.mp4). Draw layer on the paused player (object-fit-exact mapping, size labels, x delete, banner Done/Type/Cancel), per-eye SBS coords auto-mirrored with live dashed ghost, dialog pre-filled for numeric fine-tune, Draw again keeps rects. gRestorer pixelate kernel on ChitraMaya Decoder/Encoder. Output becomes preview so SBS View wipe-verifies. Shipped v1.10.00 (Batches 11-12 + New/button-state fixes). | Gman + Claude | 2026-07-17
CM-068 | P2 | Done | UI | Manage Models modal overflow on long lists (issue #3) + Esc close | First external bug: long fetched model list pushed Close off-screen (1080p and up). Modal now flex column capped 90vh, title+Close pinned, body scrolls; base .modal gets 90vh/overflow safety net for all modals; Esc closes (jobs keep running server-side, resume on reopen). Verified headless at exactly 1920x1080 with 40+30-row lists. Shipped v1.20.00 (Batch 13). | GitHub issue #3 | 2026-07-17 |  | https://github.com/seatv/ChitraMaya/issues/3
CM-069 | P2 | Done | Infra | Single-source version constant | chitramaya/__init__.py __version__ is the one line bumped per release; HF download User-Agent (ChitraMaya/<ver>) and window title read it. Replaced stale hardcoded UA. Shipped v1.20.00 (Batch 14). | Gman + Claude | 2026-07-17
CM-070 | P1 | Done | Mosaic | Auto Mosaic - NSFW-detection censor mode (EXPERIMENTAL) | Detect-and-pixelate via pluggable MosaicClipRestorer (mode=mosaic): reuses full detect/track/SBS/composite path, no restoration model needed. Surfaced as Alternate Execution Modes (Add Mosaic + Block, mutually exclusive with renamed Preview Detection) so Test Frame (Original->Censored), Restore and Restore & Save all honor it; one-shot Auto-detect in the dialog; output -censored.mp4. Field verdict: mechanics solid, lada NSFW model v1.3 (YOLO-seg, 1 class, 640) misses frames - NOT production censoring; documented experimental in README/T&C/notes. Shipped v1.20.00 (Batches 14-15). | Gman + Claude | 2026-07-17
CM-071 | P2 | Done | UI | Playback speed control on main player | Slider + readout left of SBS button; 14 multiplicative steps 0.0625x-16x (full WebView2 range), double-click resets 1x, persists across original<->preview src swaps (loadedmetadata reapply). For spotting missed mosaic frames (slow) and skimming (fast). Shipped v1.20.00 (Batch 16). | Gman request | 2026-07-17
CM-072 | P1 | Done | Detection | Evaluate FaceFusion NSFW detectors as Auto Mosaic backends | lada NSFW model misses frames and author is unreachable. FaceFusion runs three NSFW detectors (content-analyser); evaluate what each returns (class/box/mask? video-capable?), licensing, and whether any can slot into the YOLO-seg detection path or needs an adapter. Goal: raise Auto Mosaic recall toward production-usable censoring. UPDATE: evaluation complete -- see project docs ChitraMaya-CM072-NSFWDetectorEval and ChitraMaya-CM072-EraXFieldNotes. | Gman (v1.20 verdict) | 2026-07-17
CM-073 | P2 | Open | UI | Player error toast for undecodable files | Main player <video> fails silently (no error listener) on anything WebView2 cannot decode - stray .ts, HEVC without OS extensions, odd containers - shows dead Play button. Add player error handler with plain-language toast (what happened + that restoration still works + likely fix). Papercut found via .ts false alarm; also queued in Batch 13 notes. | Field testing | 2026-07-17
CM-074 | P2 | Done | SBS | SBS View projection selector (fisheye 190/200) | Viewer assumes equirect-180 LR; fisheye VR sources project wrong. Add a projection dropdown - swap is confined to the direction->UV function in the fragment shader. Documented as known limitation in v1.10/v1.20 notes. ¦¦ UPDATE 2026-09-11: Shipped as VR Projection selector (Batch 19, v1.30). | SBS viewer plan | 2026-07-17
CM-075 | P1 | Done | Encode | AV1 (NVENC) encoding support | Add av1 to the encoder codec choices (UI Encoder dropdown + --enc-codec). HARDWARE GATE: NVENC AV1 encode requires Ada (RTX 40-series) or Blackwell (50-series); Ampere 30-series cannot encode AV1 (it CAN decode via NVDEC). Work: PyNvVideoCodec AV1 encode session + settings mapping (preset/QP; bf/profile differ from HEVC), capability probe with clear unsupported-GPU error naming the fix (choose hevc/h264), remux with av01 tag + faststart, verify A/V sync path. Bonus: Chromium/WebView2 decodes AV1 natively - previews and SBS View work with NO HEVC extensions dependency. Fleet: 5060Ti + 4060 can encode; 3060s validate decode-only path. ~30% bitrate savings vs HEVC at same quality for 8K VR distribution. UPDATE: shipped in Batch 18 (AV1 NVENC). Keyframe cadence verified perfect 2.0s; AV1 release blocker cleared. | Gman request | 2026-07-17
CM-076 | P2 | Done | Mosaic | MCL cap instrument ([ClipStats] capped count) | How many clips actually HIT Max Clip Length: [ClipStats] capped=N (pct at MCL). The quality-vs-VRAM dial's instrument: capped=0 means a bigger MCL buys nothing on this content; a high pct means scenes are being chopped. Field: 74.6 pct capped at MCL 60 on real content = pro-larger-MCL datapoint for the 12GB tier. | Claude Analysis | 2026-07-23
CM-077 | P1 | Done | Mosaic | RTX Super-Res secondary restoration (2x/4x pre-paste-back) | Maxine VideoSuperRes upscales restored 256 crops 2x/4x BEFORE paste-back when the original region exceeds 256 px, so the final resize shrinks instead of stretching. Graceful fallback without RTX/nvidia-vfx; pip-TRT preload guards engine deserialization. Field verdict (matched A/B, ~4 pct wall cost): adds value -- ships RECOMMENDED. Batch 26 fixed the EOF flush that had skipped the secondary on final scenes since Batch 20. [SecStats] instrumentation (Batch 27/27b): crops seen/upscaled, largest crop px, upscaled-frame + biggest-crop seek lists in the misses JSON. | Gman + Claude | 2026-07-19
CM-078 | P1 | Done | Mosaic | Temporal stabilizer (vs_temporalfix, strength 0-3) | Flow-gated 7-frame smoothing of restored crop sequences per clip, before paste-back and before the secondary; only restored pixels touched. Vendored arch + official weights (Apache-2.0), pure PyTorch, no new deps. Container-verified ~31-33 pct temporal-variance reduction. Field verdict: KEEP -- adds quality especially on the 8GB tier where MCL 60 is forced (short clips = less temporal context = more shimmer). Weights ship bundled in the package (Batch 29) with build-ledger enforcement; user copies in models/ or next to the restoration model still override. | Gman request | 2026-07-27
CM-079 | P1 | Done | UI | Process Folder batch mode | Batch an entire folder with the current settings; warm pipeline reused across files (models load once). Queue modal with per-file rows and wide layout for long filenames, skip-existing resume with per-file WHY lines, per-file error isolation (one file's failure or GPU hang does not abort the batch), quoted-path fix, skip log. | Gman request | 2026-07-23
CM-080 | P1 | Done | Infra | Stall watchdog + PCIe link canary | Watchdog detects pipeline stalls during long/batch runs. Canary tracks PCIe link generation UNDER LOAD (links idle at Gen1 via ASPM, so idle readings are not judged -- Batch 25d): warns if the link never trains up, alarms on drops vs best seen. The watchdog.py missing-file incident closed with three tripwires: spec ledger, cold-start import, redelivery. | Gman + Claude | 2026-07-24
CM-081 | P1 | Done | Packaging | Build-time module + data ledger in spec | The spec fails the build loudly, naming exactly what to integrate, if any expected new module (batch.py, watchdog.py, console_buffer.py, winproc.py, temporalfix arch/stabilizer) or bundled data file (stabilizer weights + license) is absent from the repo -- closes the WinMerge new-file blind spot. Fired correctly on first live use (caught the missing watchdog.py). | Claude Analysis | 2026-07-26
CM-082 | P2 | Done | FOI | Test Frame result history navigator | Enlarge window keeps the last 5 results for the SAME frame: < > steppers plus numbered slots for one-click random access; per-run tooltip shows time + settings (TRT, scaler, TS, blend/feather). Stack clears when the tested frame changes. Built for knob-change A/B (e.g. scaler on/off) on an identical crop. Batches 28/28b. | Gman request | 2026-07-27
CM-083 | P2 | Open | Mosaic | Dual-GPU analysis worker (design complete, parked) | Detection offload to a second CUDA GPU; cross-GPU traffic is detection metadata only. Design doc: ChitraMaya-CM083-DualGPU-Design.md (project). Hardware staged: two 3060M 6GB conversions. Post-v1.40. | Gman + Claude | 2026-07-26
CM-084 | P1 | Done | Mosaic | Sys-RAM FrameStore offload (Off/On/Auto) | Opt-in host-memory backend for FrameStore to relieve the 8GB VRAM ceiling; Auto decides via the canary's link-generation reading (narrow/Gen1 eGPU links make paging fatal, Gen3+ survives it). Agreed and queued; post-v1.40. ¦¦ UPDATE 2026-09-11: Shipped as Store backend auto/device/host (host store proven on 4K 8GB 09-09). Auto->host decision rework = CM-175. | Gman request | 2026-07-27
CM-085 | P2 | Open | UI | Collapsible Test Frame strip | The comparison strip (Mosaic¦Restored pairs) cannot be closed once populated and takes height directly from the player ('height is precious unlike width'). Add a collapse/expand toggle; likely auto-collapsed until a Test Frame run populates it, re-collapsible afterward. Next release. | Gman request | 2026-07-28
CM-086 | P2 | Open | Mosaic | FaceFusion blend-mask artifacts | Field report: the FaceFusion (support-mask) blend creates artifacts. Ships in v1.40 release notes as a known issue worded as reported behavior ('some users have reported...'). Investigate create_support_blend_mask alpha vs the legacy rectangular blend. Parked by agreement. ¦¦ UPDATE 2026-09-11: CONFIRMED 09-11 on the 9060 XT: the facefusion (support) blend feathers inward only and adds visible noise/fringe at the paste-back edge; the AMD benchmark rows (6h51m/7h06m) were measured with it. Default stays legacy ('none'); decide: fix the support mask (dilate to the mosaic bleed + outward feather) or drop the option. Presets revert to legacy. | Field testing | 2026-07-28
CM-087 | P0 | Done | Release | v1.40.00 build + clean-machine validation | Rebuild the packaged exe with Batches 26-29 + watchdog integrated (spec ledger must pass). Clean-machine checks: [Secondary] RTX Super-Res ACTIVE, [TemporalFix] ACTIVE with no manual weight placement, a folder batch run, and -cli.exe live stdout in PowerShell. ¦¦ UPDATE 2026-09-11: v1.40.00 released 2026-07-30. | Gman + Claude | 2026-07-28
CM-088 | P0 | Done | Release | v1.40.00 release docs (SFW) | README + release notes + forum BBCode; SFW text/UI screenshots only. Must include: the 8GB law (MCL 60 + preset P5), recommended preset (scaler on, temporal stability on), -cli.exe, three-file installer download, two-pass censoring, max-recall preset, known issues (FaceFusion blend artifacts; Quest seek guidance pending CM-089). ¦¦ UPDATE 2026-09-11: v1.40.00 docs shipped 2026-07-30. | Gman + Claude | 2026-07-28
CM-089 | P3 | Open | Testing | Quest seek test: HEVC vs AV1 on-headset | PC seek + headset seek behavior comparison; the outcome is a docs line either way. AV1 keyframe cadence already verified as a perfect 2.0s (keyframe hypothesis refuted; encoder correct). | Gman + Claude | 2026-07-28
CM-090 | P3 | Done | UI | Elapsed time on Preview / Test Frame runs | CORRECTED 2026-07-28: the completion modal DOES keep the elapsed time (earlier report was mistaken). Remaining ask: add an elapsed-time display to the Preview and Test Frame flows too, so every kind of run reports how long it took. Low priority; next time the UI is touched. ¦¦ UPDATE 2026-09-11: Shipped: elapsed clocks on Preview/Test Frame (T9b _wireElapsedClocks, v1.70.00). | Gman request | 2026-07-28
CM-091 | P0 | Done | Encode | AV1 seek fix: repeated sequence headers at remux | NVENC AV1 omits repeated seq headers; encoder self-heals the IVF stream at remux. v1.40.00 (Batch 30b). | Field testing | 2026-07-29
CM-093 | P1 | Done | Infra | Intel Arc (XPU) edition, Phase 0 | XPU device path, ffmpeg/QSV decode lane, CM_HW_DECODE env switch. Shipped as ChitraMaya-Intel-ARC v1.41. | Gman + Claude | 2026-08-08
CM-095 | P2 | Done | Mosaic | Checkpoint load error message (which file / why / what to do) | Wrong or corrupt .pth surfaces as one plain message instead of a pickle traceback. v1.50.00. CM-181 extends it for the lada _full training checkpoint (mmengine). | Field testing | 2026-08-10
CM-104 | P1 | Done | Mosaic | Fixed-batch BasicVSR++ sub-engine set (any Max Clip) | One memory-lean compiled set serves every Max Clip; legacy clip-sized sets still load. v1.60.00. | Claude Analysis | 2026-08-18
CM-105 | P1 | Done | Infra | AMD ROCm edition probe + first builds | ROCm torch flavour asserted in spec; three venvs one tree. Shipped as ChitraMaya-AMD-ROCM (1.40.02 -> 1.61 -> 1.70). | Gman + Claude | 2026-08-12
CM-109 | P3 | Done | UI | Copy button on the compile log | Standing rule: every log pane has Copy. v1.50 (Batch 50). | Gman request | 2026-08-12
CM-112 | P0 | In progress | Training | Training framework (Phase A detection PoC -> B -> C restoration fine-tune -> D model hub) | Phase A/A2 detection loop proven in the frozen app; Panels 1-2 shipped hidden behind trainingUI key (v1.70.00); Phase C: recipe v1 -> ft_v0/ft_v1 trained and examined; **ft_v1 CONFIRMED 09-11 to invent structure on real studio mosaic (domain mismatch: region-proportional ROI-anchored block vs studio block fixed in screen space 2.0-2.4% H; 720p GT softness) -> OUT of every standard config; recipe v2 + ft_v2 next; exam rule: watch a full studio-mosaic restoration vs generic before any model leaves the lab.** Phase D hub spec written. Splash release after Panel 3. | Gman + Claude | 2026-08-22
CM-114 | P3 | Open | UI | Save segment preview | Save the segment preview output as a file. | Gman request | 2026-08-25
CM-119 | P2 | Open | UI | Restore button dead on an anchored range | Reported 08-30; verify on 1.70.00 before fixing. | Field testing | 2026-08-30
CM-120 | P2 | Done | Encode | TS remux candidates -> Temp folder | Temp remux beside the source failed on drive F:; candidates now [Temp, src.parent] with free-space check. v1.70.00 (T9b). | Field testing | 2026-09-02
CM-124 | P1 | Done | Encode | Progress-supervised finalize (disk-progress watchdog) | Remux supervised by output size growth, size-scaled timeout, 600 s no-growth kill. v1.61.00. See CM-174/CM-179/CM-187 for what it misreads. | Field testing | 2026-08-27
CM-125 | P2 | Done | Encode | Remux .part output + discard on failure | Half-written outputs never look finished. v1.61.00. | Field testing | 2026-08-27
CM-126 | P1 | Done | Packaging | Single-file installer fold-back for AMD/Intel | ChitraMaya-rocm-install.exe / ChitraMaya-xpu-install.exe. v1.61.00. | Gman + Claude | 2026-08-28
CM-127 | P1 | Done | Infra | Long filenames (MAX_PATH) hardening | Stem-free probe, hashed remux-cache name, shortened sidecars, clear refusal >259. v1.70.00. | Field testing | 2026-08-29
CM-128 | P1 | Done | Mosaic | Unified-memory exhaustion: restore window split-retry | XPU + <20 GB RAM -> 96-frame windows; out-of-resources retries as halves. v1.61.00 (Batch 62). | Field testing | 2026-08-30
CM-129 | P2 | Open | Infra | Zero-frame run must self-grade as failure | A run that delivered 0 frames ended status=complete. Fold into CM-153 (restored==0 handling) and CM-177 (decoder frame-count sanity). | Field testing | 2026-08-30
CM-130 | P2 | Open | UI | In-app player: HEVC extension missing -> silent black | Detect onerror and show the install-extension message. README known-issue line shipped. | Field testing | 2026-08-30
CM-131 | P0 | Done | Packaging | ffmpeg 9 compatibility (-vsync removed) + spec version gate | -fps_mode passthrough; spec refuses unknown majors and mixed pairs; majors {8,9}. v1.61.00 (Batches 63-65). | Field testing | 2026-08-30
CM-132 | P1 | Done | Infra | Self-check names the matching edition when the GPU vendor is wrong | CLI text. v1.70.00. Message-box version = CM-163. | Field testing | 2026-09-01
CM-136 | P1 | Done | Release | SHA-256 table on release pages | Public commitment (lada Codeberg thread) closed with the 1.70.00 release pages. | Gman + Claude | 2026-09-01
CM-139 | P1 | Done | Mosaic | Real-ESRGAN 4x secondary (all editions) | realesr-general-x4v3, plain torch, bundled weights. v1.70.00 (Batch 68). 09-11: cleared as the source of the 'generative' artifacts (that was ft_v1, CM-112); the ESRGAN-on run is the pending AMD quality check. | Gman + Claude | 2026-09-02
CM-141 | P3 | Done | Infra | YOLO_AUTOINSTALL=false at entry | No pip at runtime inside the frozen app. v1.70.00 (Batch 79). | Claude Analysis | 2026-09-02
CM-142 | P2 | Open | Decode | ffmpeg/QSV decode lane: per-frame PTS capture | 128 frames dropped unlocatable on one source family (no PTS on the pipe lane); NVDEC lane gap-filled the same drops. Fix shape: PTS capture on the ffmpeg lane. Relevant to CM-171 transport rework. | Claude Analysis | 2026-09-01
CM-146 | P0 | Done | Mosaic | Secondary denoise wiring (the missed last hop) | secondary_denoise now reaches the pipeline; every earlier denoise A/B had run denoise=none. v1.70.00 (Batch 74). Verdict since: ultra = no visible change at +60% restore time; default none. | Claude Analysis | 2026-09-02
CM-148 | P1 | Done | Detection | Engine imgsz mismatch: submit-time modal | Use engine size / Continue on PyTorch / Manage Models. v1.70.00 (Batch 76). | Field testing | 2026-09-02
CM-149 | P3 | Open | Infra | cudaExpandableSegments key REWORK | expandable_segments unsupported by PyTorch on Windows; map the key to max_split_size_mb / garbage_collection_threshold with an honest print. | Field testing | 2026-09-02
CM-150 | P3 | Open | Decode | TS-in-MKV sources: fallback path | Fallback reproduced flawless on all five TS mkvs both nights; decide whether to keep as-is or make the primary path handle them. | Field testing | 2026-09-02
CM-151 | P1 | Open | Detection | Engine manifest + 'Compiled (with warnings)' badge + surfaced fallback | Sidecar per engine: source hash/size, compile params incl. dynamic range, GPU/CC/TRT/torch/driver/build stamp, TRT OOM/tactic-skip counts. Badge says degraded builds; run reports PyTorch fallback; per-size engines + dynamic-range default in the mismatch modal. Driven by GitHub issue #7 (RTX 3050 4 GB). NEXT DROP. | GitHub issue #7 | 2026-09-03 |  | https://github.com/seatv/ChitraMaya/issues/7
CM-152 | P2 | Open | Mosaic | Honest miss accounting | Rename visible_miss -> clip_gap_frames; passthrough audit with a second-opinion detector labelled ESTIMATE. | Claude Analysis | 2026-09-04
CM-153 | P2 | Open | Encode | restored==0 -> lossless copy / 'No mosaic found' | Exactly zero restorations: -c copy remux and say so. Absorbs CM-129. | Claude Analysis | 2026-09-04
CM-154 | P3 | Open | Testing | Detector exam tool | Answer-key scoring against a censor run's report; disagreement sets between detectors. | Claude Analysis | 2026-09-04
CM-155 | P1 | Open | Mosaic | Planner auto-clamp (Max Clip fitted to VRAM/RAM, announced) | The OCuLink 8 GB@4K case and the AMD MCL-180 case. CM-175 folds in. | Field testing | 2026-09-04
CM-156 | P3 | Open | UI | Nits bundle | Detection-rate line in summary/progress modal; cancel-at-zero-frames litter; PCIe canary baseline label; encoder remux stderr utf-8; nvGPUMonitor python_rss for frozen exe; Free-VRAM button / fresh process per VRAM row. | Claude Analysis | 2026-09-04
CM-157 | P2 | Open | UI | Compile failure hygiene | [compile] FAILED with likely cause instead of PyInstaller's 'Unhandled exception' dialog (forum screenshots 09-06). | Field testing | 2026-09-06
CM-158 | P2 | Open | Training | Model hub: safetensors only | Community models distributed as safetensors; no pickle. Phase D spec. | Claude Analysis | 2026-09-06
CM-159 | P2 | Open | Training | Model hub: ONNX detectors, not .pt | Detectors published as ONNX. Phase D spec. | Claude Analysis | 2026-09-06
CM-160 | P2 | Open | Training | Model hub: in-app fetch + hash verify | models.json registry as hash authority; PR-based review. Phase D spec. | Claude Analysis | 2026-09-06
CM-161 | P2 | Done | UI | Edition label in window title and banner | 'ChitraMaya 1.70.00 -- AMD edition'. v1.70.00 (T9b). | Gman request | 2026-09-07
CM-162 | P2 | Done | Release | README AMD section from in-house testing | Rewritten against measured numbers (T8b/T9h). 09-11: needs the Restoration-FP16 / facefusion / ft_v1 corrections once the ESRGAN-on run is watched. | Gman + Claude | 2026-09-07
CM-163 | P0 | Done | Infra | GPU gate before the window opens (wrong-edition message box) | Child-process device probe before torch; MessageBoxW naming the GPUs and the matching edition; exit 3; .gpu-gate-ok cache. v1.70.00 (T9c-2). | Field testing | 2026-09-07
CM-164 | P2 | Done | UI | TRT toggles hidden on non-CUDA editions | data-edition gate. v1.70.00 (T9b). The scaler dropdown was missed -> CM-184. | Gman request | 2026-09-07
CM-165 | P2 | Done | Packaging | .cmd launchers capture ERRORLEVEL and pause with guidance | v1.70.00 (T9b). | Gman request | 2026-09-07
CM-166 | P3 | Open | Infra | ROCm self-check cosmetic: 'failed to run offload-arch' warning | First line of every ROCm start. Suppress or explain. | Field testing | 2026-09-07
CM-167 | P0 | Done | Encode | AMF encoder probe frame too small (every AMD user encoded on the CPU) | Probe 640x360 nv12; failing probe prints its first stderr line. v1.70.00 (T8a). segB 27m44s -> 10m25s. | Field testing | 2026-09-07
CM-168 | P1 | Done | Infra | MIOpen cache pinned next to the exe | Survives updates; first-run compile notice. v1.70.00 (T9b). | Field testing | 2026-09-07
CM-169 | P0 | Done | Detection | ROCm forces Detection FP16 off | FP16 detection stops detecting after the first frames on the 9060 XT. Greyed with reason. v1.70.00 (T8a). Restoration FP16 was left live on a 270-frame test -> CM-186. | Field testing | 2026-09-07
CM-170 | P3 | Done | Infra | ultralytics settings sync=False | v1.70.00 (T9b). | Claude Analysis | 2026-09-07
CM-171 | P0 | Open | Decode | Decode transport: Windows anonymous pipe is the wall (AMD + Intel) | -probe-decode named it: decoder 447 fps, pipe 37-39 fps @1080p; 63% of the AMD wall, 60% of Intel. Fix: 64 MB pipe buffer (_winapi.CreatePipe) or named pipe; PyAV in-process as fallback rung. Expected AMD ~7h -> ~5h50m, Intel -3.5h. rocDecode-for-Windows on STANDING WATCH. NEXT DROP. | Claude Analysis | 2026-09-07
CM-172 | P0 | Done | Mosaic | Per-shape MIOpen compiles in the blend mask (22-hour AMD collapse) | conv2d/avg_pool2d -> summed-area box filter, verified to 2.5e-5 vs legacy. v1.70.00 (T9a). Intel: -21% restore on segB. | Field testing | 2026-09-08
CM-173 | P1 | Done | UI | Saved configurations (presets) in the gear menu | Whole-panel snapshots, one-click load, save-as/delete modal. v1.70.00 (T9e/T9f/T9g). Run-report 'panel' block reuses the schema (CM-180). | Gman request | 2026-09-08
CM-174 | P1 | Open | Encode | Remux watchdog vs +faststart in-place rewrite | No-growth kill on ~20 GB+ outputs during the faststart pass. Count mtime as progress + faststart allowance -- OR moot once CM-187 removes the pass. NEXT DROP (decide with CM-187). | Field testing | 2026-09-09
CM-175 | P1 | Open | Mosaic | 4K VRAM reserve + Auto -> host when the RAM plan fits | Reserve omits decoder 16-frame buffer (~400 MB @4K), NVENC surfaces (~300 MB), region transients; Auto picks host only when headroom < 0. Folds into CM-155. NEXT DROP. | Field testing | 2026-09-09
CM-176 | P2 | Open | Infra | faulthandler.enable() at the frozen entry | Native faults write the Python stack to the console log (drive-F: silent exit case). NEXT DROP. | Field testing | 2026-09-09
CM-177 | P2 | Open | Decode | Decoder frame-count sanity check per file | Demuxer count vs container duration wildly apart -> stop the FILE with 'source unreadable -- check the drive', continue the batch. Absorbs CM-129. NEXT DROP. | Field testing | 2026-09-09
CM-178 | P1 | Open | Packaging | Per-edition build/dist folders | build-<edition>/dist-<edition> via spec workpath/distpath + the three .ps1; packager prints which tree it wrote. The NVIDIA patch zip existed only because NVIDIA was built last. NEXT DROP. | Gman request | 2026-09-10
CM-179 | P0 | Open | Infra | Keep-awake held through finalize | pipeline.run releases the claim before EOF flush/remux -> machine sleeps during long remux (mux=2316 s on two machines). Also hold ES_DISPLAY_REQUIRED (see CM-188). NEXT DROP. | Field testing | 2026-09-10
CM-180 | P1 | Open | Infra | Run report replaces the misses JSON (spec written) | <stem>.run.json: 'panel' = the control panel exactly as submitted (preset schema; 'Load settings from a run...'), 'effective' = asked/ran/reason for every forced field, structured timing, counts, events, per-frame lists as ranges, whole console to <stem>.log; runReport = beside¦temp¦off. Absorbs CM-185. Spec: claude/ChitraMaya-CM180-RunReport-Spec.md. Three OPEN decisions for Gman. User request (forum) for the off switch. NEXT DROP. | Gman request | 2026-09-10
CM-181 | P2 | Open | UI | lada _full.pth = training checkpoint: label/skip + mmengine message | Manage Models lists all 17 lada files; 'download all, compile all' pulls the 287 MB training checkpoint (needs mmengine, never shipped). Label it, skip it in Compile All, loader message names mmengine. From GitHub issue #7's class of user. NEXT DROP. | GitHub issue #7 | 2026-09-10 |  | https://github.com/seatv/ChitraMaya/issues/7
CM-182 | P1 | In progress | UI | Multi-language UI | Strings table + data-i18n + language key; console stays English; ask which language; community translations via the hub. ¦ 2026-09-14: FIRST TRANSLATIONS RECEIVED -- zh-CN and zh-TW (CSV + JSON), 342/342 keys, no empties, placeholders intact, 11 entries legitimately untranslated (FPS, FP16, HEVC, IoU, SBS, data.yaml, FB/FF); zh-TW is a real localization (64/342 identical to zh-CN), not a script conversion. Remaining work is ours: language switch + string loader in the UI (data-i18n on the extracted keys), fallback to English per key, RTL not needed yet. Gman moved to P1. | User request (forum) | 2026-09-10
CM-183 | P2 | Open | Detection | Compile defaults scaled to free VRAM | Fixed max-batch 8 / workspace 2 GB overflow 4 GB cards (TRT OOM tactic skips). Derive from free VRAM; expose in the compile modal. NEXT DROP. | GitHub issue #7 | 2026-09-10 |  | https://github.com/seatv/ChitraMaya/issues/7
CM-184 | P1 | Open | UI | Hide RTX Super-Res on AMD/Intel; RTX -> ESRGAN fallback | rtx-2x/4x offered on every edition; on AMD the request fails and the run continues with NO secondary after one warning line; NVIDIA-saved configs carry it in. Remove on rocm/xpu, map to esrgan-4x with a console line, fall back to ESRGAN (not nothing) when the RTX runtime is missing. NEXT DROP. | Field testing | 2026-09-10
CM-185 | P2 | Open | Infra | Echo blend mask in the request line and the run report | Absorbed by CM-180. | Field testing | 2026-09-10
CM-186 | P2 | Open | Mosaic | Restoration FP16 fence on ROCm + non-finite/black output guard (all editions) | ROCm forces restoration FP16 off (greyed + reason, like CM-169); every edition checks each restored chunk for non-finite / all-zero before paste-back -> redo in FP32 + warning + report event. Black-box cause NOT confirmed as FP16 (see CM-188); this is defence in depth. README/notes currently say Restoration FP16 'works and is your choice' and the toggle defaults on -> correct with the drop. NEXT DROP. | Field testing | 2026-09-11
CM-187 | P1 | Open | Encode | One-pass finalize (audio extracted at run start; no vtmp; no faststart rewrite) | Finalize makes 9 whole-file passes on NVIDIA / 7 on AMD-Intel (~150 GB of disk traffic for a 31 GB 4K output) -> watchdog kills -> hand-fix every 4K remux. Extract audio once to <stem>.audio.mka (ride the ffmpeg decode pass on AMD/Intel); A/V offset via setts bsf on the stream-copied raw input (fallback -ss on audio); faststart via reserve_index_space (fallback none). 9->3 / 7->3 passes; CM-174 moot; RECOVER no longer needs the source. Verify per edition on segB (offset + no-offset) and one 4K on the Dell. Gman: discuss after the AMD investigation. | Gman + Claude | 2026-09-11
CM-188 | P2 | Open | Infra | Detect GPU device reset / power event during a run; hold display-required | Black boxes + waviness appeared only in two UNATTENDED overnight AMD runs; no settings combination reproduces them (40-min, 45-min, full-title re-runs clean). Working theory: display-off / power-state / driver TDR (Event 4101 amdkmdag) / Windows Update mid-run -> VRAM undefined, process survives. Check Event Viewer for the two windows. Fix: ES_DISPLAY_REQUIRED + system-required while running; detect device reset and abort loudly rather than continue with corrupted memory. | Field testing | 2026-09-11
CM-189 | P2 | Open | Infra | Linux port (clone + pip + python -m chitramaya) | Code is largely OS-neutral (pathlib; engine suffix .win/.linux already exists). Windows couplings confined to winproc.py, keep_awake.py, gpu_gate.py (MessageBoxW + WMI), self_check.py (powershell GPU inventory), rtx_secondary.py (guarded). Gaps: pywebview needs GTK/Qt or a browser-only mode; hwaccel ladder lacks cuda/vaapi (lands on CPU decode); Maxine unavailable (optional). Plan: (1) sandbox smoke test with CPU torch -- import surface, -self-check, browser-mode UI, jsdom -- next release cycle; (2) driver-install walkthrough with Gman on the dual-boot box (Ubuntu 24.04 LTS; 9060 XT stays in the 3600XT box on PCIe 4.0 x16; 5600 + 32 GB coming from Seattle); (3) guards + hwaccel + docs/linux.md; (4) Linux release at some point, no date. Note: 63 unique cloners/14 days, spiking on push days = mostly automated cloners; some are people. | Gman + Claude | 2026-09-11
CM-190 | P0 | Done | Decode | MPEG-TS temp remux failed silently since v1.61 (.part suffix hid .mp4 from ffmpeg) | The CM-125 .part suffix made ffmpeg 'unable to choose an output format' for the CM-120 CFR temp, so every TS source was NVDEC-decoded directly with drops (head skip + gap-fill duplicates). Fixed 09-12 (T10a-2); remux temp in Temp; one console line names it. | Field testing | 2026-09-12
CM-191 | P0 | Done | Mosaic | Re-decode frame source (no frame store): second NVDEC decoder re-produces frames at paste-back time | Frames are not stored; the primary decoder feeds detection and cropping, a lagging Decoder on the same source (same backend/args; owns the TS remux temp) re-produces each frame when it is due for blend+encode. Alignment by frame number with PTS check (skip/freeze/count-only, counted). store_backend auto¦redecode¦device¦host; auto -> redecode on NVDEC (not VR projection / Test Frame). Field: byte-identical output vs the device store on PurpleRain, segB and a 4-min dense 4K cut; 2.8x faster than the device store on 8 GB; VRAM 11.06 -> 7.86 GB on the 12 GB box. Design note: claude/ChitraMaya-CM191-RedecodeDesign.md. Shipped T10c/T10d/T10d-2. | Gman + Claude | 2026-09-12
CM-192 | P2 | Open | Mosaic | Auto clip window (goodbye MCL): cut clips at natural boundaries under a measured VRAM/quality ceiling | With frames free (CM-191) Max Clip Length no longer costs memory; cut clips at track end / TTL / shot change under an internal ceiling from the restorer's measured per-frame VRAM cost and a quality ceiling measured with ab_eval_noref at 60/120/180/300/600 on segB. Splash candidate; after CM-191 is proven on the Dell. | Gman + Claude | 2026-09-12
CM-193 | P0 | Done | Mosaic | Pending patches at clip resolution (unpad+resize at blend time) | Redecode patches were held at FRAME resolution: one 180-frame clip of 2400-px regions = 3.1 GB -> the x16 8 GB run died at 59 % (CM-122). Patches now keep the restorer output at clip resolution (post-secondary, pre-unpad/resize); unpad+resize+blend run together at drain, same ops same order -> bit-identical. ~570 MB per 180-frame clip with RTX 4x, ~47 MB without. Shipped T10d. | Field testing | 2026-09-13
CM-194 | P1 | Done | UI | Console drawer duplicated the startup block (overlapping polls) | One /api/console poll in flight at a time; an answer for a cursor already moved past is dropped. Shipped T10d. | Field testing | 2026-09-13
CM-195 | P1 | Done | Infra | Timestamped process console log, newest 20 kept | ChitraMaya-console-YYYYMMDD-HHMMSS[-pid].log in the app folder; older than the newest 20 deleted at launch; first console line names the file. Companion: CM-180 run report (<stem>.run.json + <stem>.log per run; runReport beside¦temp¦off). Shipped T10d. | Gman | 2026-09-13
CM-196 | P0 | Field testing | Mosaic | 8 GB VRAM oversubscription with the full stack: patches to pinned RAM, prefetch trims, VRAM ledger | Three NVENC error-8 deaths of one 4K60 title on 8 GB cards at its 2400-px regions; monitor: VRAM pinned at 7.9 GB from the first hour, WDDM paging 4 GB/s over OCuLink, 1.5-2 fps for 23 min before the lock failed. Fix (T10e, 3f68fee): pending patches wait in pinned host RAM (redecodePatches host¦device, default host; byte copies, bit-exact); lag prefetch 8 -> 4 frames; primary NVDEC prefetch 2x batch (min 8) on cards < 10 GB; [VRAM] ledger lines (after models / first drain / end) with other = used - torch_reserved, vram column on every 500-frame checkpoint and in the run report; torch cache released after drains (rate-limited); run_error carries the exception text; effective.det_imgsz / redecode_patches. Field gate: segB device vs redecode on the Dell, then the full title with the monitor. If it still dies: the ledger names the next lever (denoise ultra / SS 4x footprint). | Field testing | 2026-09-14
CM-197 | P1 | Open | Mosaic | Two-pass restoration with a resumable plan (detect once, restore many; resume a dead run) | Pass 1: decode + detect + track only -> a PLAN file: frame numbers, boxes, clip boundaries, masks (RLE/PNG or polygons; geometry only, no content, SFW by construction). Pass 2: decode + crop from the plan + restore + blend (lag decoder) + encode. Unlocks: RESUME a run that died mid-title from the plan at the last encoded frame (no other tool does this); detect once / restore N times with identical boxes for A/B; clip boundaries chosen with the whole timeline known (feeds CM-192); exact ETA from frame one; plan reusable by the CM-154 detector exam. Cost: one more NVDEC pass of the title (3 decodes instead of 2; the background engine, largely hidden) + plan I/O; detection is NOT repeated -- net wall time about even, possibly better from unbroken batches. Design questions: mask payload format; plan invalidation (source hash, detector model/imgsz/conf); resume = re-encode from plan + concatenate or continue the raw bitstream; UI: 'Resume' on a dead run's report. Gman 09-14: 'resume will be a great feature to have' -- schedule after prioritization, after T10e is proven. | Gman + Claude | 2026-09-14
CM-198 | P2 | Open | Infra | nvGPUMonitor run trigger: monitor starts/stops with the run, CSV lands beside the run report | Today the monitor is started by hand and its CSV spans more than the run, so every analysis begins by slicing the window (the 09-14 Dell forensics) and half-runs get half a CSV (SegB-256 started midway). Integrate: the pipeline starts nvGPUMonitor at run start (a 'monitor' marker row) and stops it at finalize, CSV written as <stem>.monitor.csv beside <stem>.run.json; config key runMonitor on¦off (default off until the exe ships with the app or its path is configured; monitorPath); the run report records monitor file + PCIe link (max_gen x cur_width) so the dial is right by construction. Also folds in the 09-14 monitor fixes: PCIe dial denominator = max_gen x cur_width (was max_gen x max_width: 15.76 GB/s shown for a Gen3 x4 link); per-sample NVML tx/rx peaks exceed the link maximum -> smooth or label; decoder/encoder util read 0 on OCuLink eGPUs -> mark n/a rather than 0. Gman 09-14: 'do we have a roadmap item to integrate nvGPUMonitor trigger?' -- no, this is it. | Gman + Claude | 2026-09-14
CM-199 | P1 | Open | UI | Model hub: selectable Hugging Face endpoint (hf-mirror.com for China mainland) + automatic fallback | GitHub issue #13: huggingface.co needs a VPN from mainland China and is slow; hf-mirror.com is a free, fast reverse proxy with identical paths (/api/models/<owner>/<repo>/tree/main, /resolve/main/<file>). Our downloader hard-codes https://huggingface.co in three places (server.py: tree listing, resolve URL, token rule). Change: one endpoint value -- config key hfEndpoint in ChitraMaya-config.json (default https://huggingface.co), a dropdown in the model hub dialog (huggingface.co ¦ hf-mirror.com (China mainland) ¦ custom URL); model-sources.json keeps canonical huggingface.co URLs and the host is swapped at fetch time; the hf-token is sent only to the configured endpoint host; console line names the endpoint per download. Auto-fallback: a connection failure/timeout on huggingface.co retries once on hf-mirror.com and says so. Honouring HF_ENDPOINT as a default source is optional (Gman decides; env-var doctrine). README sentence in the Models section + zh-CN/zh-TW strings for the new dropdown (CM-182). Half a day; verify_ui_js/ui_smoke gates (dialog change). | GitHub #13 | 2026-09-14

## Next Drop (proposed)
Order | ID | Title | Why now | Size | Needs from Gman
1 | CM-179 | Keep-awake through finalize | Two machines slept during the remux; trivial change | hours | -
2 | CM-187 | One-pass finalize | Every 4K remux hand-fixed; removes CM-174's failure mode | 1-2 days | OPEN: discuss after AMD; approve the design
3 | CM-186 | Restoration FP16 fence + black-output guard | Defence in depth; docs say the opposite today | half day | Confirm ESRGAN-on run looks right
4 | CM-184 | Hide RTX on AMD/Intel, ESRGAN fallback | Silent no-secondary runs from imported configs | hours | -
5 | CM-180 | Run report (panel + effective) | Could not tell what ran; user asked for the off switch | 1-2 days | 3 OPEN decisions in the spec
6 | CM-171 | Pipe transport | 63% of the AMD wall, 60% of Intel | 1 day + measurement | AMD box available for segB before teardown?
7 | CM-175 / CM-155 | VRAM reserve + Auto->host / planner clamp | Dell 8GB@4K died twice on the device store | 1 day | -
8 | CM-151 + CM-183 | Engine manifest, warnings badge, compile defaults from VRAM | GitHub issue #7 open on it | 1-2 days | -
9 | CM-181 | _full checkpoint label/skip + mmengine message | Same user class as #7 | hours | -
10 | CM-176 / CM-177 | faulthandler + decoder frame-count sanity | Drive-F: silent exit | half day | -
11 | CM-178 | Per-edition build/dist | Release-day lesson | hours | -
12 | hwDecode key | Config key -> CM_HW_DECODE | Env-var doctrine; README documented a key that never existed | hour | -
13 | CM-086 | Facefusion blend: fix or drop | Confirmed noise source 09-11 | half day | Decide fix vs drop
14 | misc | CM-166; probe prints cuda on ROCm; errored-run decoder warning | nits | hours | -
15 | CM-188 | Device-reset detection + display-required | Depends on the Event Viewer finding | half day | Event Viewer check for the two overnight windows

## Updates
Roadmap brought forward from CM-090 (2026-07-28) to CM-188 (2026-09-11).
Existing rows updated: CM-046/061/074/084/087/088/090 -> Done; CM-047 -> superseded by CM-151; CM-062 -> largely superseded; CM-086 -> P1, confirmed 09-11.
CM IDs known to be parked but whose titles were not recovered in this pass: CM-092, 094, 096-102, 106-108, 110-111, 113, 115-118, 121-123, 133-135, 137-138, 140, 143-145, 147. Fill from the batch notes or drop.
Status values used: Done / Open / In progress. Priorities are PROPOSED for new rows; Gman decides.
'Next Drop (proposed)' is an ordering for review, not a commitment. Items marked NEXT DROP in the Description column match it.
Release rule (09-11): no release without watching and approving a full studio-mosaic restoration on each edition released.
Phase C rule (09-11): no model leaves the lab on numbers alone -- watch a full studio-mosaic restoration vs generic first.
2026-09-14: rows CM-190..CM-197 added (post-release drops T10a..T10e). Statuses: 190/191/193/194/195 Done in the field; 196 Field testing (T10e built, Dell gate pending); 192 Open; 197 NEW -- two-pass plan + resume, added at Gman's request 09-14, to be prioritized.
2026-09-14: CM-186 shipped as the black-output guard only (no FP16 fence -- no proof FP16 hurts restoration on AMD); CM-187 + CM-179 shipped in T10a (one-pass finalize). Mark Done when the release goes out.
2026-09-14 PM: CM-198 added (nvGPUMonitor run trigger + the PCIe dial fix). 256/512 study on segB: 512 = poor reconstruction with the generic v1.2 weights -> a larger clip needs its own trained weights (Phase C); recorded in the day state.
2026-09-14 PM (merge): Gman's priority changes kept (CM-038 P1, CM-182 P1; CM-083/086/186/188 -> P2); CM-182 -> In progress with the zh-CN/zh-TW delivery noted. CM-198 was already in Gman's copy.
2026-09-14 PM: CM-199 added from GitHub issue #13 (hf-mirror.com endpoint for the model hub).